## Sheet1
TECHNICAL RISK SUMMARY SHEET FOR : |  |  |  | Severity |  |  |  | Probability |  |  |  | Risk
|  |  |  | 1 | Negligible: | Extremely low cost or no injuries. |  | 1 | Infrequent: | Very unlikely to occur |  | 1 to 3 | Insignificant: |  | No significant determined risk present
Patient Risks During Treatment |  |  |  | 2 | Minor: | Low cost or minor injuries. |  | 2 | Possible: | Could occur, but unlikely |  | 4 to 6 | Minor: |  | Risks remain, but are not considered significant
ACTIVITY: |  |  |  | 3 | Serious: | High cost or serious injuries. |  | 3 | Probable: | May well occur |  | 8 to 9 | Significant: |  | A significant risk remains
Risk Analysis |  |  |  | 4 | Critical: | Extremely high cost or loss of life. |  | 4 | Frequent: | Will probably occur |  | 12 to 16 | Major: |  | A major risk remains
Ref. No. | Risk Description | Initial Risk Evaluation |  |  | Risk Assessment |  | Risk Mitigation Undertaken |  |  |  | Residual Risk Evaluation |  |  | Subsequent Risks & Mitigation |  | Additional Risk Evaluation
|  | Severity | Probability | Risk | [6 empty] | Severity | Probability | Risk |  |  | Severity | Probability | Risk
1 | Carbon dioxide poisoning: Low O2 concentration | 3 | 3 | 8 | If the oxygen concentrator has a component failure (mechanical, electrical) or spent zeolite then the O2 concentration may drop below desired levels. |  | Alarms will sound detecting that O2 concentration fails below limit. SpO2 blood monitoring devices may also sound alarms. Operator reads the diagnostic message ir printed instructions attached to the device and intervenes |  |  |  | 2 | 2 | 6 | We need to train operators to respond to alarms promptly |  | 2 | 2 | 4
1 | Carbon dioxide poisoning: Low O2 flow | 3 | 3 | 8 | If the compressor has a mechanical or electrical failure or the oxygen concentrator has a component failure (mechanical, electrical) then the O2 flow may drop below desired levels. |  | Alarms will sound detecting that O2 flow fails below limit. SpO2 blood monitoring devices may also sound alarms. Operator reads the diagnostic message ir printed instructions attached to the device and intervenes |  |  |  | 2 | 2 | 6 | We need to train operators to respond to alarms promptly |  | 2 | 2 | 4
3 | Operator Incapacitation | 3 | 2 | 8 | O2 concentrator fails or external compressor fails and alarms may sound, but nobody is present to react |  | Proactively check the device to ensure functionality within parameters |  |  |  | 2 | 2 | 5 | we need to train maintenance personnel to monitor the device functionality periodically |  | 2 | 2 | 4
5 | Fire Risk through Fuel (O2) | 4 | 1 | 12 | Fires or sparks caused by other activities may cause ignition of canula or O2 concentrator |  | Use O2 compatible materials in all involved components and also around the canula and O2 output. |  |  |  | 4 | 1 | 9 | Need to train medical personnel to avoid any source of fires |  | 4 | 1 | 8
6 | Patient Regaining Consciousness
7
8
9
9 | Fire Risk through Heat
9 | Fire Risk through Oxygen
9
10
11